## Sheet1
Phase | Activities | Start Week
Phase 1 | Literature review, model selection, requirement analysis | Week 1
Phase 2 | Facial recognition pipeline development | Week 3
Phase 3 | Voice recognition pipeline development | Week 4
Phase 4 | Pipeline integration and decision fusion | Week 7
Phase 5 | Anti-spoofing implementation (Liveness Detection) | Week 9
Phase 6 | Model Quantization and Optimization (QAT) | Week 11
Phase 7 | Hardware deployment, testing, evaluation, and documentation | Week 14